## Sheet1
System Name： | Trade Finance
Module Name： | Local letter of guarantee
ID | Steps to reproduce the bug | Status | Expected Result | Actual Result | Scheduling Date | Latest test Date | delivery date | Note
1 | Letter of Guarantee->local letter of guarantee event->fill all required fields(general case)->Commision details | Pass | the commission of guarantee amount should be calculated automatcally. | the commission filled manually. | 2024-03-05 | 2024-03-18 | 2024-03-18
2 | Letter of Guarantee->local letter of guarantee event->fill required fields(general case)-> Letter of Guarantee Type field | Pass | the options of type of guarantee field:Bid Bond, Performance, Advance payment, other | there other different options that are needless. | 2024-03-05 | 2024-03-17 | 2024-03-17
3 | Letter of Guarantee->local letter of guarantee event->fill required fields(general case)->view voucher | Pass | in voucher, the account name of credited liabilty account should be 'Bank Liability'. | the account name of credited liabilty account currently is 'Beneficiary Liability'. | 2024-03-06 | 2024-03-17 | 2024-03-17
4 | Letter of Guarantee->local letter of guarantee event->fill required fields(general case)->LG Amount Details | pending | the amount in arabic needs correction. | the amount in arabic is not correct. | 2024-03-06 | 2024-03-06 |  | we have provided the development team with the way to present the amount in arabic
5 | local letter of guarantee event-> creation mode->fill the required fields->fill the Subject/Reason of LG field. | pending | Subject/Reason of LG field should enble me to type more charecters. | the allowed number of charecters is small and not efficient | 2024-03-11 | 2024-03-11 |  | this field usually filled by pages of charecters.
6 | local letter of guarantee event-> creation mode->Approved limit field & UnUtilized Amount. | pending | the values of these two fields should be related to the facility account of this customer. | the values of these two fields are related to limit value of this customer. | 2024-03-12 | 2024-03-12 |  | we have agreed that we do not have such as this practice(guarantee limit on the customer account) but may this customer has a facility account and this facility account has an approved limit)
7 | local letter of guarantee event-> creation mode | pending | no need to these fields:'Additional Conditions', 'Document and Presentation Instructions', 'Principal's Instructions to Bank', so to be removed. |  | 2024-03-13 | 2024-03-13
8 | local letter of guarantee event-> creation mode->fill the required fields->save | pending | the successful message should contains the account number and lg reference. | the successful message currently contains only the account number. | 2024-03-13 | 2024-03-13 |  | the LG reference like this:''
9 | Letter of Guarantee->Letter of Guarantee-Invoke->creation mode->Charges Debit Account field | pending | in this field, no need for this lablel 'margin debit account number' to be apeared. | in this field, lablel 'margin debit account number' is existed. | 2024-03-13 | 2024-03-13
10 | Letter of Guarantee-> Letter of Guarantee - Claim event-> Mail/Approval Date field & Mail/Approval No. | pending | these two fields should be filled automatically with issuance date and no, with the ability to edit it. | currently, we couldnot edit them. | 2024-03-13 | 2024-03-13
11 | Letter of Guarantee-> Letter of Guarantee - Claim event | Fail | upload docs to DMS. | there is no document button for this. | 2024-03-13 | 2024-03-31
12 | Letter of Guarantee-> Letter of Guarantee - Claim event->creation mode->Margin Amount field. | pending | this field should be Always changing according to the invoked amount. | currently, this filled constant and is not affected by the invoked amount. | 2024-03-14 | 2024-03-14
13 | Letter of Guarantee-> Letter of Guarantee - Claim event->creation mode->Charges Debit Account Number field. | Pass | this field should be optional for the case in which we do not need charges in claim event. | currently, this field is mandatory. | 2024-03-14 | 2024-03-31
14 | Local LG Amendment->creation mode-> date of issue field. | Pass | this field should be disabled, to prevent the user from editing the issue date | currently, this field is editable. | 2024-03-19 | 2024-03-24 | 2024-03-24
15 | Local LG Amendment-> creation mode-> guarantee type field | Pass | this field should be disabled, to prevent the user from editing the type of guarntee | currently, this field is editable. | 2024-03-19 | 2024-03-24 | 2024-03-24
16 | Letter of Guarantee->Local LG Amendment->Adjust type ->Reference Details section | pending | all fields in Reference Details secion should be disabled for Adjust | currently most of these fields are enabled | 2024-03-24 | 2024-03-24
17 | Letter of Guarantee->Local LG Amendment->Adjust type ->Margin Details section | pending | in adjust mode, it is supposed to prevent the user to edit the margin | currently, margin is editabe with Adjust | 2024-03-24 | 2024-03-24
18 | Letter of Guarantee->Local LG Amendment->Amend type ->Reference Details section | pending | all fields in Reference Details section should be disabled for Amend, Except for: Date of Expiry, Subject/Reason of LG , Other Remarks | currently most of these fields are enabled | 2024-03-24 | 2024-03-24
19 | Letter of Guarantee->Local LG Amendment ->Amend type ->Beneficiary Details section | pending | for Amend Type, we can not edit the beneficiary details | we can edit it in Adjust mode only. | 2024-03-24 | 2024-03-24
20 | Letter of Guarantee->Local LG Amendment ->Amend type ->Commission Details section | Fail | the total commission amount should be for new commission (not for the whole lg commission starting from issuing event) | you view the commission starting from issuing event | 2024-03-24 | 2024-03-31 |  | we know that you do it correctly in voucher,but as business practice, bank team suggested this.
21 | Letter of Guarantee->Local LG Amendment ->Amend type ->increase the LG amount. | pending | it is supposed, to calculate the commission for each increased amount sepratelly. | you donot take any commission for the newly increased amount. | 2024-03-24 | 2024-03-24
22 | Letter of Guarantee->creation mode | pending | when we fill the undertaking amount, a kind of validation is needed that is the UnUtilized Amount of facility account should be equal or greater than the whole LG amount, but without preventing the user to complete the event(In other words:the user needs a warning just to inform him about that UnUtilized Amount less than the whole LG amount with the ability to complete the event) |  | 2024-03-27 | 2024-03-27
23 | Letter of Guarantee Expiry event(cancel, expire,close ) | pending | mail date & mail number fields should be available. | currently are not existed. | 2024-03-27 | 2024-03-27
24 | Letter of Guarantee Expiry event-> creation mode | pending | Issuing Bank Details & Receiving Bank(BIC) & Advising Bank fields are meaningless in local LG(to be removed) | these sections are existed as disabled fields. | 2024-03-27 | 2024-03-27
25 | Letter of Guarantee Expiry event-> creation mode | Pass | (21) Related Reference No' field is needeless(should be removed) | currently is existed. | 2024-03-27 | 2024-03-27
26 | Letter of Guarantee Expiry event-> creation mode | Pass | view swift message' button is meaningless in local LG(should be removed) | currently is existed. | 2024-03-27 | 2024-03-27
27 | Letter of Guarantee Expiry event(cancel, close)-> creation mode | pending | (21) Related Reference No' field is needeless(should be removed) | currently is existed. | 2024-04-02 | 2024-04-02 |  | Note:when I mention Local LG Expiry event, I mean the expiry as event not expiry status
28 | Letter of Guarantee Expiry event(cancel)-> creation mode | pending | view swift message' button is meaningless in local LG(should be removed) | currently is existed. | 2024-04-02 | 2024-04-02
29 | Letter of Guarantee Expiry event(cancel)-> creation mode ->(22A) Purpose Code field | pending | this field should be removed for local gurantee | currently is existed. | 2024-04-02 | 2024-04-02
30 | Letter of Guarantee Enquiry -> fill the Date range -> customer -> fill specific LG refernce -> cllick view-> view the details specific stage. | pending | margin amount field, arabic beneficiary name, customer name, outstanding liability amount, all these field are requested in this event. | none of them is existed. | 2024-04-02 | 2024-04-02
31 | Letter of Guarantee Enquiry -> fill the Date range -> fill customer field -> cllick view. | pending | the amount field in all retreived records should changes with the current stage. | currently it is fixed for all stages. | 2024-04-02 | 2024-04-02 |  | for instance, we have an LG has these events: iss =100000 . Claim =5000 . Invoke=5000 . Claim=2000 . The amount field should contains the previous amounts as per the stage.
32 | Local Letter of Guarantee event ->creation mode -> use facility account -> margin <100%. | pending | the commission should be calculated automatically. | currently no commission viewed. | 2024-04-02 | 2024-04-02
33 | Local Letter of Guarantee event ->creation mode -> use facility account -> margin <100% -> view voucher. | pending | in voucher, the commission should be credited to commission account | for the case in which we use facility account you debit the comm without crediting it. | 2024-04-02 | 2024-04-02
34 | Letter of Guarantee->Local LG Amendment -> mail Date field. | pending | it is supposed, to be able to fill this field by previous date. | currently, we can not do it. | 2024-04-03 | 2024-04-03
35 | Letter of Guarantee->Local LG Amendment -> change the facility account disicion to NO. | pending | we expect to remind me to cover the LG totally | currently we can remove the facility account without covering the LG by 100 % mgn. | 2024-04-03 | 2024-04-03
36 | Letter of Guarantee->local letter of guarantee issue event & amendment event | pending | user should be able to enter the the margin amount and the percentage will be generated according to the entered value(in addition to the available ability to enter the percentage and then get the margin amount). | currently, user can enter the percentage and then get the amount as per this percentage | 2024-04-04 | 2024-04-04