## Sheet1
System Name： | Trade Finance
Module Name： | Import bills
NO | Steps to reproduce the bug | Status | Note | Scheduling Date | Latest test Date | delivery date
1 | primary details event | Pass | for IBLS bill type, in delivery against field, an additional 'free of payment' option is needed. | 2024-02-04 | 2024-02-27 | 2024-02-27
2 | adivse of payment withMT202 message type(unavailable this type) | Pass | should be available in primary details event in message type field | 2024-02-04 | 2024-02-27 | 2024-02-25
3 | advise of payment | Pass | 1- we are in need to field for drawee account to be more flexable with the debited account. | 2024-02-04 | 2024-04-14 | 2024-04-14
4 | MT410 ack | Pass | 72 field is not reflected to the swift. | 2024-02-05 | 2024-03-18 | 2024-03-18
5 | MT416 | Pass | no entries viewed (the liability and the custom charges should be reversed). | 2024-02-06 | 2024-03-24 | 2024-03-24
6 | primary details event(USD bill currency). | pending | in voucher the currency of debited custom charges should be in USD. | 2024-02-06
7 | expiry bill | pending | not working. | 2024-02-06
8 | we made MT416 then MT400 | Fail | we expect the required bill is not available in MT400(because we already applied MT416 on it). The same thing if we make MT416 then MT412. | 2024-02-06 | 2024-03-31
9 | MT430 amendment | pending | check it, no correct swift and no correct voucher. | 2024-02-11
10 | advise of payment with MT103 | Pass | intermediary Bank should be exsited and optional. | 2024-02-14 | 2024-03-17 | 2024-03-17
11 | advise of payment | Pass | in this event, MT400 message type is needed as well as MT202 & MT103. | 2024-02-14 | 2024-02-27 | 2024-02-27
12 | primary details event | Pass | the case in which delivery against= free of payment then the field 'from event ' and 'due date' should be disabled because we don't havepayment absolutely. | 2024-02-18 | 2024-03-31 | 2024-03-31
13 | advise of payment:the case in which, we select full bill in primary details event, then pay part of bill amount, it is confliction | Pass | we expect warning should appear. | 2024-02-25 | 2024-02-25 | 2024-03-25
14 | import bills enquiry. | Fail | no options in stage field | 2024-02-25 | 2024-02-25 |  | unknown options
15 | import bills enquiry. | pending | the results of this enquiry should be related to the stage (event) not to whole bill. Also when clich on view button of this event(resulting from the enquiry), the retrieved fields must refere to the event values(not the whole bill values). | 2024-02-25 | 2024-02-25
16 | import bills with delivery against='free of payment' then try to pay it | Pass | should prevent the user to pay it, because it is 'free of payment' | 2024-02-27 | 2024-03-25 | 2024-03-25
17 | primary details event, with delivery against='payment' | Fail | fields 'from event' and 'Due Date' should be disabled | 2024-03-03 | 2024-04-14
18 | primary details event, adding document details. | Pass | in 'Document Details' section,description field, we need 'invoice' option to be added | 2024-03-03 | 2024-03-17 | 2024-03-17
19 | primary details event | Pass | the name of sections 'charges' & 'drawer details' should be reversed(in vice versa) | 2024-03-03 | 2024-03-17 | 2024-03-17
20 | primary details | Pass | the label of fields '(20)Sender's Reference No./SWIFT' & '(21)Reference No./Bill No.', to be 'Sender's Reference No' & 'Reference No./Bill No.'. | 2024-03-03 | 2024-03-18 | 2024-03-18
21 | primary details | Pass | document details: we have the following scenario: as you know, the document usually recieved in two sets(or two mails) or more, so we need for each document to mention the original and the copies in each mail separately, this case is not possible to do now. so i can suggest the best way to implement it, we want to change the field 'number of set' to be drop list and its name 'mail number' or 'set number'. in this case we can input the details of specific document, by selecting the required document from description field, and then select the mail number from drop list then enter the original and the copy of received and office copy and add them,and then repeat the input for the second mail. | 2024-03-03 | 2024-03-17 | 2024-03-17
22 | primary details | Pass | address2 & address3 to be optional | 2024-03-03 | 2024-03-17 | 2024-03-17
23 | primary details, mode of transport, filling multiple mode of transport | Pass | bank team usually adds multiple modes of transport, so we need list of check box to select multiple modes. | 2024-03-03 | 2024-03-17 | 2024-03-17
24 | primary details,'document type' field | Pass | to be optional | 2024-03-03 | 2024-03-17 | 2024-03-17
25 | primary details | Pass | from port' label to be 'from' & 'to port' label to be 'to'. 'goods description' label to be 'goods category'. | 2024-03-03 | 2024-03-17 | 2024-03-17
26 | primary details | Pass | the values of 'Account Name' column in voucher: for debited customer libility account to be'customer liability account', for credited correspondent liability account to be 'correspondent liability account'. | 2024-03-03 | 2024-03-18 | 2024-03-18
27 | primary details, search for specific bill | Pass | the 'Bill No' column is always blank. | 2024-03-03 | 2024-03-25 | 2024-03-25
28 | primary details, non finance payment. | Pass | for non finance, the field link facility should be disabled. | 2024-03-03 | 2024-03-17 | 2024-03-17
29 | advice of acceptance MT412 | Pass | all the disabled field to be in gray color. | 2024-03-03 | 2024-03-17 | 2024-03-17
30 | advice of acceptance MT412 | pending | the OUP charges need configuration. | 2024-03-03 | 2024-03-11
31 | advice of payment, with MT202 option to pay. | Pass | 53a, 54a, 57a, 58a, all of them are not reflected correctly to MT202 message. | 2024-03-03 | 2024-03-18 | 2024-03-18
32 | advice of payment, with MT400 option to pay. | Pass | 53a, 54a, 57a, 58a, all of them are not reflected correctly to MT400 message. | 2024-03-03 | 2024-03-18 | 2024-03-18
33 | advice of payment. | pending | the OUP charges need configuration. | 2024-03-03 | 2024-03-03
34 | advice of non-acceptance after we have already paied | Pass | should warn me(or prevent the user to apply like this scenario). | 2024-03-03 | 2024-03-26 | 2024-03-26
35 | advice of non-acceptance MT416. | Pass | all disabled fields in 'Bill Lodgment details' section to be in gray color. | 2024-03-03 | 2024-03-17 | 2024-03-17
36 | acknowledgment MT410(normal case) | pending | charges need confugration, no currency, no debit acccount, no rate type, no exchange rate. | 2024-03-05 | 2024-03-05
37 | primary details event, filling the mail date and decision date by advaced date | Pass | it should warn me, that this date in future. | 2024-03-05 | 2024-04-01 | 2024-04-01
38 | primary details event. | Pass | custom certificate security charge should be removed from primary details event and place it in payment and to be optional. | 2024-03-05 | 2024-03-31 | 2024-03-31
39 | primary details event. | pending | INCO term field to be removed | 2024-03-05 | 2024-03-17 |  | this field is meaningless in import bills.
40 | primary details event. | Fail | Import LIC/OGL, License Number, License Date, Permit Number, Permit Issue , all of them to be moved to payment event, not used in primary details event. | 2024-03-05 | 2024-03-17 | 2024-03-17 | you made them optional, so will check it with the concerned staff
41 | primary details event, receipt date field, fill it with any previous date. | Pass | it prevents me to fill it with previous date(this date usually is the same as mail date), and give me this warning'receipt date can not be less than booking date'. | 2024-03-05 | 2024-03-25 | 2024-03-25
42 | primary details event. | Pass | document type field to be optional. | 2024-03-05 | 2024-03-17 | 2024-03-17
43 | primary details event. | Pass | the label 'board date', change it to 'shipment date'. | 2024-03-05 | 2024-03-17 | 2024-03-17
44 | primary details event. | Pass | we are in need to 'bill of lading date'field to be added. | 2024-03-05 | 2024-03-17 | 2024-03-17
45 | primary details event. | pending | advising and postage commission to be found by default in OUP charge. | 2024-03-05 | 2024-03-05
46 | advice of payment. | Pass | in purpose code field, just we need a single option 'goods value'(add it as another option). | 2024-03-06 | 2024-03-18 | 2024-03-18
47 | primary details event. | Pass | Bill No format is not correct, it should be like this: IDC0106000324 | 2024-03-06 | 2024-03-17 | 2024-03-17
48 | advise of payment | Pass | 'nostro number' and 'nostro credit account' should be 'correspondent number' and 'correspondent credit account' . | 2024-02-04 | 2024-03-14 | 2024-03-14
49 | primary details event, for the option 'From B/L Date' and 'After B/L Date' in From Event field. | Pass | the value of due date field should be calculated starting form the 'bill of lading date' field. | 2024-03-17 | 2024-03-17 | 2024-03-25
50 | primary details event-> Document Details section->Description field | Pass | in this field we need the option 'invoice' | 2024-03-17 | 2024-03-18 | 2024-03-18
51 | advise of payment-> MT103 message type | Pass | intermediary Bank should be exsited and optional. | 2024-03-17 | 2024-03-25 | 2024-03-25
52 | advise of payment-> MT202 message type | Pass | 71B and 73 fields are not needed in this type of message. | 2024-03-17 | 2024-03-24 | 2024-03-24
53 | acknowledgment MT410 ->reference details section. | Pass | the fields of 'refernce details' section should be disabled and gray (we do not need to edit it). | 2024-03-17 | 2024-03-24 | 2024-03-24
54 | primary details -> view mode-> Document Details section->Remarks field | Pass | for the case in which we leave it blank, it will be filled automatically by 'undefined' value. | 2024-03-17 | 2024-04-01 | 2024-04-01
55 | primary details event-> Document Details section->number of set field | Pass | the label of this field should be 'mail number' | 2024-03-18 | 2024-04-01 | 2024-04-01
56 | payment event , with MT400 type, fields 20 & 21 | Pass | the values of these two fields should be in vice versa, because 20 refers to sender reference and 21 refers to receiver reference, and also in swift message should be in vice versa. | 2024-03-18 | 2024-03-25 | 2024-03-25
57 | payment event -> Message Type=MT202 | Pass | for this type of message, we need a new field to specify the receiver of this message, and this field should be reflected to the swift message. | 2024-03-18 | 2024-04-01 | 2024-04-01 | the receiver is not reflected to the swift
58 | payment event -> Message Type=MT202 | pending | in swift message, sender field is needed and should refers to sender(comm bank of syria in our case) bydefault(the same as in MT400). | 2024-03-18 | 2024-04-01 |  | you are considering the sender always is the ordering bank, but if you look at the swift, we see that the ordering bank is optional and it is used only to specifies the ordering financial institution when other than the Sender of the message.
59 | payment event -> Message Type=MT202 | Pass | 58a field should be mandatory | 2024-03-18 | 2024-03-24 | 2024-03-24
60 | payment event -> Message Type=MT400 | Pass | for this type of message, we need a new field to specify the receiver of this message, and this field should be reflected to the swift message. | 2024-03-18 | 2024-04-01 | 2024-04-01 | the receiver is not reflected to the swift
61 | payment event -> Message Type=MT400 | Pass | 52 should be optional | 2024-03-18 | 2024-03-25 | 2024-03-25
62 | payment event -> Message Type=MT202 | Pass | 52 should be optional | 2024-03-18 | 2024-03-25 | 2024-03-25
63 | payment event -> Message Type=MT400 | Fail | 32a, 33a these fields should contain the value date in swift message | 2024-03-18 | 2024-04-14
64 | primary details event->fill all fields with mode of transport ->save | Pass | failed to save | 2024-03-18 | 2024-03-26 | 2024-03-26
65 | advise of acceptance->20 & 21 fields | Pass | the values of these two fields should be in vice versa, because 20 refers to sender reference and 21 refers to receiver reference, and also in swift message should be in vice versa. | 2024-03-20 | 2024-03-25 | 2024-03-25
66 | advise of acceptance->beneficiary bank field | Pass | this field is not needed in this event, should be removed. | 2024-03-20 | 2024-03-24 | 2024-03-24
67 | advise of acceptance-> Receiver Bank Details secion | Pass | the label 'Applicant Bank' should be 'Receiver Bank', and 'Applicant Bank Branch' should be 'Receiver Bank Branch'. | 2024-03-20 | 2024-03-24 | 2024-03-24
68 | Import Bill Primary Details->creation mode ->finance Payment Type->select facilty account. | pending | when select the facility account we want two fields to show the limit and utilized amount of this facility account, the same as in local guarantee | 2024-03-20 | 2024-04-14
69 | paying finance Bill(this customer has a facility account) | Fail | in payment event, it is supposed to debit the customer account by the value that filled manually and debit the remaining amount from the faciltiy account, with taking into your consideration the case in which we have syp facility account and pay foreign currency Bill so we want to take the equavalent of paid amount from the facility account. | 2024-03-20 | 2024-04-14
70 | primary details event, with the acceptance type, for the option 'From B/L Date' and 'After B/L Date' in From Event field. | Pass | the value of due date field should be calculated starting from the 'bill of lading date' field and affected by usanse days. | 2024-03-25 | 2024-04-01 | 2024-04-01
71 | payment event , with MT202 type, fields 20 & 21 | Pass | in swift message the values of these two fields are not reflected correctly(in vice versa). | 2024-03-25 | 2024-03-31
72 | MT 416 Advice of Non-Payment/Non-Acceptance ->71F:Charges Currency / Amount field | Pass | this field is not related to '32A: Face Amount of Documents' section and should not be putted under it(we expect to be in separte section). | 2024-03-25 | 2024-03-31 | 2024-03-31
73 | MT 416 Advice of Non-Payment/Non-Acceptance -> Reference Details section | Fail | (20) Sender's TRN No' & '(21) Related Reference No'are in vice versa(reverse the values of them), and also should be reflected correctly to the swift | 2024-03-25 | 2024-03-31
74 | Import Bill Primary Details-> creation mode -> Mode of transport field | Pass | the hint of this field is wrong (the number of selected options that appear as hint) | 2024-03-27 | 2024-04-01 | 2024-04-01
75 | MT400 Advice Of Payment -> creation mode ->MT202 or MT400 msg type | pending | field (58a) Beneficiary Bank, when we leave it blank, in this case no need to be reflected to the swift message. | 2024-03-27 | 2024-03-27
77 | advice of payment event -> creation mode ->Custom Certificate Details section. | Pass | Custom Certificate Number field is not wanted | 2024-03-27 | 2024-04-01 | 2024-04-01 | when we take custom certificate charges in payment , we do not have the custom certificate at all, the question now how can I know the custom certificate number?? So this field should be removed.
78 | Refund of Custom Security Amount event ->creation mode | Fail | the entries of voucher is not correct. | 2024-03-27 | 2024-03-31
79 | advise of acceptance | pending | there a missed scenario about the case of reserving margin for acceptance bill, and this scenario mentioed in separte file sent by mail in this date. | 2024-03-27 | 2024-03-27
80 | advise of acceptance event -> creation mode | pending | field '72. Sender to Receiver Information', when we leave it blank, in this case no need to be reflected to the swift message. | 2024-03-28 | 2024-03-28
81 | Import Bill Primary Details-> creation mode -> Document Details section ->number of set field | pending | this field is not wanted, should be removed. | 2024-04-02 | 2024-04-02 |  | bank team refused this field, and asked to be removed.
82 | Import Bill Primary Details-> authorization mode(reviwer). | Fail | approve button should be named 'review'. | 2024-04-02 | 2024-04-14