## Sheet1
System Name： | Trade Finance
Module Name： | Inward letter of guarantee
ID | Steps to reproduce the bug | Status | Expected Result | Actual Result | Scheduling Date | Latest test Date | delivery date | Note
1 | Letter Of Guarantee Inward event | pending | a new separete field beside the '(20)Undertaking Number' field for the correspondent letter date to fill it manually. | no like this field. | 2024-05-22 | 2024-05-22
2 | Letter Of Guarantee Inward event->date of issue field. | pending | to be able to select previous date. | we can not select previous date. | 2024-05-22 | 2024-05-22
3 | Letter Of Guarantee Inward event -> 23B field. | pending | should be extracted automatically from the inward swift. | this field is blank(not extrated) | 2024-05-22 | 2024-05-22
4 | Letter Of Guarantee Inward event ->39A tolerance details. | pending | no like this field in MT760. | currently is implemented. | 2024-05-22 | 2024-05-22
5 | Letter Of Guarantee Inward event ->35G field. | pending | this field 12*65x, should be extracted completely from the swift message. | extracted with some missed lines. | 2024-05-22 | 2024-05-22
6 | Letter Of Guarantee Inward event ->44J field. | pending | no 44J field (should be replaced with 44H), and this field should take its value from the swift as it is. | there is 44J instead of 44H. | 2024-05-22 | 2024-05-22
7 | Letter Of Guarantee Inward event ->45L. | pending | this field 50*65z should be extracted from the swift message with all lines. | currently only the first line is extracted. | 2024-05-22 | 2024-05-22
8 | Letter Of Guarantee Inward event ->57a. | pending | this field is optional. | mandatory. | 2024-05-22 | 2024-05-22
9 | Letter Of Guarantee Inward event ->22Y. | pending | this field should takes its value according the swift message. | 22Y takes value bydefault regardless what it is in the swift. | 2024-05-22 | 2024-05-22
10 | Letter Of Guarantee Inward event | pending | comission section to be implemented. | no commission section now. | 2024-05-22 | 2024-05-22
11 | Letter Of Guarantee Inward event. | pending | MT799 swift to be implemented at the issue event, | no like this message in this event. | 2024-05-22 | 2024-05-22
12 | Letter Of Guarantee Inward event -> creation mode-> fill LG details ->save. | pending | this LG should take a new serial reference number. | it takes the same correspondent reference number. | 2024-05-22 | 2024-05-22
13 | LG invoke event-> field Nostro acccount. | pending | the label of this field to be 'Correspondent account'. | it is nostro account. | 2024-05-26 | 2024-05-26
14 | LG invoke event-> field recovered amount | pending | the label of this field to be 'invoke amount' | currently is recovered amount, even we do not have margin in inward LG. | 2024-05-26 | 2024-05-26
15 | LG invoke event->creation mode. | pending | charges section is needed. | currently not implemented. | 2024-05-26 | 2024-05-26
16 | LG invoke event->creation mode. | pending | MT799 is needed, at the same event. | missed. | 2024-05-26 | 2024-05-26
17 | LG invoke event->creation mode. | pending | document button to be enabled to upload docs. | currently missed in this event. | 2024-05-26 | 2024-05-26
18 | enquiry event -> search for inward LG. | pending | the ability to find it. | can not find it. | 2024-05-26 | 2024-05-26