## Sheet1
System Name： | Trade Finance
Module Name： | Import letter of credit
Test Case | Import letter of credit
NO | Test scenario | Status | Note | Scheduling Date | Latest test date | Delivery date
1 | lc pre-advise(the normal scenario) | Pass | the bank team needs an ability to select multiple mode of transport, so we suggest if we have list of checkboxes for multiple modes. | 2024-02-04 | 2024-04-04 | 2024-04-04
2 | lc pre-advise(the normal scenario) | Pass | 1- the oup code and narration of charges are reversed. 2- goods description and 79Z fields:unable to leave spaces between the words. 3- new field for receiver should be existed and reflected in the swift. 4- an ability to save the event as draft without filling all the fields. | 2024-02-05 | 2024-04-04 | 2024-04-04
3 | lc advise event(the normal scenario) | Pass | inco term field:CIP to be added. | 2024-02-06 | 2024-05-13 | 2024-05-13
4 | lc advise event(the normal scenario) | Pass | 1- 48 narrative field should be longer. | 2024-02-06 | 2024-02-25 | 2024-02-25
5 | lc advise event(the normal scenario) | Pass | 1- in lc amount details:32B, the label of currency field should be currency and the label for amount should amount(two different labels for the two fields). 2- 51a should be optional. 3- 57a: should be optional. | 2024-02-06 | 2024-02-25 | 2024-02-25
6 | lc advise event(the normal scenario) | Pass | 46A field:no ability to break the line. | 2024-02-07 | 2024-04-14 | 2024-04-14
7 | lc advise event(the normal scenario) | Pass | 48 field :should be reflected to the swift. | 2024-02-07 | 2024-02-25 | 2024-02-25
8 | lc advise event(the normal scenario) | pass | 1-address2 and address3 to be optional. 2- margin details: 'margin debit account number' label to be 'customer debit account number'. 3- the label of 41a should be 'available with... by...' | 2024-02-07 | 2024-02-25 | 2024-02-25
9 | lc advise event(the normal scenario) | Pass | 46A: when we break the lines, the new lines are not reflected in the swift, it consider all of them as a one line.(please check the event fields and how to reflected in the swift avoiding of like this bug). | 2024-02-08 | 2024-04-14 | 2024-04-14
10 | lc advise event(the normal scenario) | Pass | 1- 43T field: beside this field, the bank team needs a disabled(by default) narrative field, and this field is enabled only for 'conditional' and 'allowed' options, and should be reflected in the swift beside the value 43T. | 2024-02-08 | 2024-02-25 | 2024-02-25 | warning should apeare for 'conditional' or 'allowed' options only, not for 'not allowed'.
11 | lc advise event(the normal scenario) | pass | 1- receiver bank is unavailable, bank team needs fields to fill the detials of the receiver bank, and should be reflected in the swift (important point), and the label of this field should be 'receiver'. | 2024-02-08 | 2024-02-25 | 2024-02-25
14 | bill lodgment (document presentation) | pending | correspondence letter date: should be blank and fill manually. | 2024-02-11
15 | bill lodgment (document presentation) | Pass | license date field: should be disabled. | 2024-02-11 | 2024-04-21 | 2024-04-21
16 | lc advise event(the normal scenario) | pending | we need Custom Certificate Details fields (the same as in bill lodgment),also in advise event, and this custom Certificate Details should be optional and enabled 'only' for the private sector account(as agreed we suppose that already specified the type of account 'public' or 'private' when we define the account, so this will help us to make a decision for this custom certificate). | 2024-02-12
17 | bill lodgment (document presentation) | Pass | document details: we have the following scenario: as you know, the document usually recieved in two sets(or two mails) or more, so we need for each set to mention the original and the copies in each mail separately, this case is not possible to do now. so i can suggest the best way to implement it, we want to change the field 'number of set' to be drop list and its name 'mail number' or 'set number'. in this case we can input the details of specific document, by selecting the required document from description field, and then select the mail number from drop list then enter the original and the copy of received and office copy and add them,and then repeat the input for the second mail. | 2024-02-12 | 2024-05-13 | 2024-05-13
18 | bill lodgment (document presentation) | Pass | FOB value to be optional. | 2024-02-12 | 2024-03-31 | 2024-03-31
20 | bill lodgment (document presentation) | Pass | remove 'payment type' field from this event. | 2024-02-13 | 2024-04-24 | 2024-04-24
21 | bill lodgment (document presentation) | Pass | custom certificate details fields should be optional and configurable. | 2024-02-13 | 2024-03-06 | 2024-03-06
23 | lc payment. | Pass | the label 'Nostro Bank Name' :should be 'Correspondent Name'. The label 'Nostro Credit Account' :should be 'Correspondent Credit Account'. | 2024-02-15 | 2024-04-14 | 2024-04-14
24 | lc amendment | pending | the case in which we had 'reimbursing bank' in issuance event, then when amend the lc we need MT747 to be generated in addition to MT707 at the same event. | 2024-02-15
25 | lc amendment after bill lodgment event | Pass | now we could not apply amendment after bill lodgment, but we are in need to amend the lc after bill lodgment. | 2024-02-20 | 2024-04-21 | 2024-04-21
26 | acknowledgment MT730 | pending | this event is not existed now, we need it. | 2024-02-20
27 | amendment event | Pass | in this event, the field channel should be gray. | 2024-02-20 | 2024-05-13
28 | bill lodgment | Pass | 1-goods category field should be in issuence event, so remove it from bill lodgment and move it to issuance. 2-the fields:'Country Of Origin, Place Of Origin, Import LIC/OGL, License Number, License Date, Permit Number, Permit Issue Date, INCO Terms, Mode Of Transport, From Port and To Port', all of them imported as it is from issuance event and filled automatically, so in addition to they are filled automatically, we want to be disabled(gray) because these information taken from issuance event without any change and to prevent the user from edit it. | 2024-02-22 | 2024-04-21 | 2024-04-21
29 | lc advise event(the normal scenario) | Pass | receiver bank recently added: the labels of this field should be 'receiver bank' and 'receiver bank branch' instead of 'applicant bank' & 'applicant bank branch'. | 2024-02-28 | 2024-04-14 | 2024-04-14
30 | lc advise event(the normal scenario) | Pass | the allowed length of licence number field should be at least 9 charecters | 2024-03-06 | 2024-04-14 | 2024-04-14
31 | lc pre-advise(the normal scenario) | Pass | 57a, BIC code filed should be optional. | 2024-02-04 | 2024-03-31 | 2024-03-31
32 | lc pre-advise(the normal scenario) | pending | the definitions of voucher columns should be as the following: a-the case of local currency -for swift charge: narration field of DR account should be customer account and the narration field of CR account should be swift charge -for postage charge: narration field of DR account should be customer account and the narration field of CR account should be postage, mail, telegraph, teleph.. commission. b-the case of foreign currency: -for swift charge: narration field of DR account should be customer account. -for postage charge: narration field of DR account should be customer account. | 2024-02-05
33 | lc advise event(the normal scenario) | Pass | 45A, 46A, 47A, 49G, 49H, 78: in these fields we are unable to leave spaces between the words. | 2024-02-06 | 2024-04-14 | 2024-04-14
34 | lc advise event(the normal scenario) | Pass | 45A field(goods tolerance) should be removed. | 2024-02-06 | 2024-04-14 | 2024-04-14
35 | Letter of Credit Pre - Advice[MT705] event -> creation mode -> sight type. | Pass | for this lc type, it is supposed only 'payment' to be available in Payment Term. | 2024-04-23 | 2024-05-13 | 2024-05-13
36 | Letter of Credit Pre - Advice[MT705] event -> creation mode -> usance type. | Pass | for this lc type, it is not acceptable for 'payment ' option to be available for selection here. | 2024-04-23 | 2024-05-13 | 2024-05-13
37 | Letter of Credit Pre - Advice[MT705] event -> creation mode -> mode of transport field. | Pass | the hint over this field is not correct. | 2024-04-23 | 2024-05-13 | 2024-05-13
38 | Letter of Credit Pre - Advice[MT705] event -> review mode -> reject it. | Pass | when reject it, nothing rejected, the event will authorized. | 2024-04-23 | 2024-05-12 | 2024-05-12
39 | Letter of Credit Pre - Advice[MT705] event -> creation mode ->Charge Type. | Pass | the option 'RECEIVED' to be 'BEN'. | 2024-04-23 | 2024-05-12 | 2024-05-12
40 | Import LC Bill Lodgement->Delivery Against field. | Pending | Delivery Against field, is entered in issue event at whole LC level, and we can not edit in lodgment event, so this field to be removed. | 2024-04-23 | 2024-04-23
41 | Import LC Bill Lodgement | Pass | field '20' does not accept the charecters '/' or '-' | 2024-04-28 | 2024-05-12 | 2024-05-12
42 | Import LC Bill Lodgement | pending | Document Date to be the same as Correspondant Letter Date by default. | 2024-04-28 | 2024-04-28
43 | LC payment | Pass | save as draft option is needed in payment event. | 2024-04-28 | 2024-05-12 | 2024-05-12
44 | Import LC Bill Lodgement | Fail | 20sender reference is our reference, it should be or ILC reference bydefault. | 2024-04-29 | 2024-05-12 | 2024-05-12
45 | MT734 advise of refusal | pending | 20 field should be filled automatically with our lc reference number. | 2024-04-30 | 2024-04-30
46 | MT734 advise of refusal | Pass | 77B, to be list of codes, instead of filling it manually. | 2024-04-30 | 2024-05-23 | 2024-05-23
47 | advise of payment | pending | 20 should be our reference (ILC reference),21 should be the corresponadnt reference. | 2024-04-30 | 2024-04-30
48 | advise of payment | pending | 23 field is not reflected to the swift message. | 2024-04-30 | 2024-04-30
49 | advise of payment | Pass | field 30 is not existed, and should be refelected to the swift message. | 2024-04-30 | 2024-05-12 | 2024-05-12
50 | Import LC Bill Lodgement | pending | field 30 date of disacrpancies is needed in lodgment event. | 2024-04-30 | 2024-04-30
51 | advise of payment | Pass | reseiver field is needed. | 2024-04-30 | 2024-05-12 | 2024-05-12
52 | advise of payment | Pass | the value date to be bydefault after 2 days from the curent date. | 2024-04-30 | 2024-05-12 | 2024-05-12
53 | Letter of Credit enquiry | Pass | in stage field, no option to filter by Bill lodgment. | 2024-05-08 | 2024-05-12 | 2024-05-12
54 | Letter of Credit enquiry | pending | when select for some events, reference number & account id column should refere to the reference number & account id for the current event not for the ILC reference or ILC account id. | 2024-05-08 | 2024-05-08
55 | lc advise event | pending | when save the LC as draft, the status of this LC apeare as authorized and is not correct. | 2024-05-08 | 2024-05-08
56 | Import LC Bill Lodgement | pending | bank team is looking forward to have the ability to refuse the received documents at the same 'Bill Lodgment' event(which means to send MT734 at the same lodgment event). | 2024-05-08 | 2024-05-08 |  | missed implemetaion(not bug)
58 | Import LC Bill Lodgement | pending | bank team is looking forward to have the ability to send MT799 at the same event if they want. | 2024-05-08 | 2024-05-08 |  | missed implemetaion(not bug)
56 | in amendment event | pending | when select amend type, the serial number of 'number of adjustment' field should is not affected by the this type of amend. | 2024-05-13 | 2024-05-13
57 | lc advise event(the normal scenario) | Pass | 2- mode of transport: multiple mode required(the same as pre-advise). | 2024-02-06 | 2024-05-13 | 2024-05-13