## Sheet1
System Name： | Trade Finance
Module Name： | Local letter of guarantee
ID | Steps to reproduce the bug | Status | Expected Result | Actual Result | Scheduling Date | Latest test Date | delivery date | Note
1 | Letter of Guarantee->local letter of guarantee event->fill all required fields(general case)->Commision details | Pass | the commission of guarantee amount should be calculated automatcally. | the commission filled manually. | 2024-03-05 | 2024-03-18 | 2024-03-18
2 | Letter of Guarantee->local letter of guarantee event->fill required fields(general case)-> Letter of Guarantee Type field | Pass | the options of type of guarantee field:Bid Bond, Performance, Advance payment, other | there other different options that are needless. | 2024-03-05 | 2024-03-17 | 2024-03-17
3 | Letter of Guarantee->local letter of guarantee event->fill required fields(general case)->view voucher | Pass | in voucher, the account name of credited liabilty account should be 'Bank Liability'. | the account name of credited liabilty account currently is 'Beneficiary Liability'. | 2024-03-06 | 2024-03-17 | 2024-03-17
4 | Letter of Guarantee->local letter of guarantee event->fill required fields(general case)->LG Amount Details | pending | the amount in arabic needs correction. | the amount in arabic is not correct. | 2024-03-06 | 2024-03-06 |  | we have provided the development team with the way to present the amount in arabic
5 | local letter of guarantee event-> creation mode->fill the required fields->fill the Subject/Reason of LG field. | pending | Subject/Reason of LG field should enble me to type more charecters. | the allowed number of charecters is small and not efficient | 2024-03-11 | 2024-03-11 |  | this field usually filled by pages of charecters.
6 | local letter of guarantee event-> creation mode->Approved limit field & UnUtilized Amount. | pending | the values of these two fields should be related to the facility account of this customer. | the values of these two fields are related to limit value of this customer. | 2024-03-12 | 2024-03-12 |  | we have agreed that we do not have such as this practice(guarantee limit on the customer account) but may this customer has a facility account and this facility account has an approved limit)
7 | local letter of guarantee event-> creation mode | pending | no need to these fields:'Additional Conditions', 'Document and Presentation Instructions', 'Principal's Instructions to Bank', so to be removed. |  | 2024-03-13 | 2024-03-13
8 | local letter of guarantee event-> creation mode->fill the required fields->save | pending | the successful message should contains the account number and lg reference. | the successful message currently contains only the account number. | 2024-03-13 | 2024-03-13 |  | the LG reference like this:''
9 | Letter of Guarantee->Letter of Guarantee-Invoke->creation mode->Charges Debit Account field | pending | in this field, no need for this lablel 'margin debit account number' to be apeared. | in this field, lablel 'margin debit account number' is existed. | 2024-03-13 | 2024-03-13
10 | Letter of Guarantee-> Letter of Guarantee - Claim event-> Mail/Approval Date field & Mail/Approval No. | pending | these two fields should be filled automatically with issuance date and no, with the ability to edit it. | currently, we couldnot edit them. | 2024-03-13 | 2024-03-13
11 | Letter of Guarantee-> Letter of Guarantee - Claim event | pending | upload docs to DMS. | there is no document button for this. | 2024-03-13 | 2024-03-13
12 | Letter of Guarantee-> Letter of Guarantee - Claim event->creation mode->Margin Amount field. | pending | this field should be Always changing according to the invoked amount. | currently, this filled constant and is not affected by the invoked amount. | 2024-03-14 | 2024-03-14
13 | Letter of Guarantee-> Letter of Guarantee - Claim event->creation mode->Charges Debit Account Number field. | pending | this field should be optional for the case in which we do not need charges in claim event. | currently, this field is mandatory. | 2024-03-14 | 2024-03-14