## Sheet1
System Name： | Trade Finance
Module Name： | Import letter of credit
Test Case | Import letter of credit
NO | test scenario | Status | Note | Scheduling Date | latest test date | delivery date
1 | issue a new lc with multiple quarters | pass | fixing the commission in issuance event for multiple quarters | 2024-01-23 | 2024-01-29 | 2024-01-29
2 | bill lodgment event with complied documents | pass |  | 2024-01-23 | 2024-01-28 | 2024-01-28
3 | amendment event: increase the lc amount. | F | the commission must be calculated correctly for the new increasing amount for the remaining quarters. | 2024-01-23 | 2024-02-19
4 | amendment event: extend the lc. | F | the commission must be calculated correctly for the new quarters that we entered in after amendment. Special case: suppose we have lc with expiry date 5 months, then extended it 15 days,in this case we didn't enter in a new quarter,so the commossion must still as it is. | 2024-01-23 | 2024-02-19
5 | advice of refusal MT734 | pending | could not complete it. | 2024-01-23
6 | make payment from facility account | pending | in voucher: the debited facility acount must be in the same facility account's currency and the payment amount must be splited between the margin account and facility account. | 2024-01-24
7 | reimbursing bank field is filled in issuance event | F | MT740 must be generated to send it to reimbursing bank(in addition to MT700) and this MT740 appears at the same page beside the MT 700 at the first step of authorization. | 2024-01-24 | 2024-02-19
8 | amendment event: extend and increase at the same time. | F |  | 2024-01-25 | 2024-02-19
9 | benenificiary approval event | F | voucher entries to be fixed. | 2024-01-25 | 2024-02-19
10 | paying complied documents (payment). | pending | no need to generate MT752(just for non complied docs need this). | 2024-01-28
11 | cancel lc | Pass | it is ok, but we will leave the final decision to bank team(especially for the decision if we want to return the commission or not). | 2024-01-28 | 2024-02-22 | 2024-02-22
12 | close lc | Pass | it is ok, but we will leave the final decision to bank team(especially for the decision if we want to return the commission or not). | 2024-01-28 | 2024-02-22 | 2024-02-22
13 | lc issuance with tolerance | Pass | small note:the commission must be calculated basing on the whole amount of lc plus the tolerance(not only for the amount of lc). For instance:the lc amount 1000000 USD and the tolerance 10%=10000 then the commission should calculated on 1000000+10000 | 2024-01-28 | 2024-03-11 | 2024-03-11
14 | amendment event: any type of lc amend | pending | needs configured correctly 200EUR not 20EUR. | 2024-01-30 | 2024-02-19
15 | MT732 advise of discharge | Pass | is not working (we could not complete it). | 2024-01-30 | 2024-02-25 | 2024-02-25
16 | expire lc | Pass | it is ok, but we will leave the final decision to bank team. | 2024-02-04 | 2024-02-22 | 2024-02-22
17 | reinstate lc | Pass | it is ok, but we will leave the final decision to bank team. | 2024-02-04 | 2024-02-22 | 2024-02-22
18 | lc issuance with deferred type of payment | F | in this case, a new field 42P should be enabled to fill it (check the swift category). | 2024-02-07 | 2024-03-11 | 2024-03-11
19 | lc issuance with mixed-payment type of payment | F | in this case, a new field 42M should be enabled to fill it (check the swift category). | 2024-02-07 | 2024-03-11 | 2024-03-11
20 | lc payment, with MT 752 swift type. | pending | 23field: this field includes specific options(accept, debit, negotiate..) configure it. | 2024-02-11
21 | payment event,click f2 to search for a payment | pending | the authorization status of payments always be authorized, check it for the other status. | 2024-02-25
22 | advise of amendment extension MT708 | pending | 1-field '30 date of amend' is disabled and not filled , it should be filled automatically or editable and filled manually. 2-no MT708 swift generated. | 2024-02-25 | 2024-02-25
23 | lc enquiry | pending | the results of this enquiry should be related to the stage (event) not to whole amount. Also when clich on view button of this event(resulting from the enquiry), the retrieved fields should refere to the event values(not the whole lc values). | 2024-02-25 | 2024-02-25
24 | MT732 advise of discharge, with adding of OUP charges. | pending | OUP charges are not defined | 2024-02-25 | 2024-02-25
25 | lodgment event on defferred usanse lc. | pending | for option 'from bill of lading date' in 'from date' field: due date should be based on the bill of lading date field(shipping date). | 2024-02-26 | 2024-02-26
26 | lc advice event, with usanse type | pending | fields 'usance days' & 'usance from' are not reflectrd to the swift, it should be placed in the swift beside the 'available by' field. | 2024-02-28 | 2024-02-28
27 | lc advice event, with usance type | pending | in usance from field, we need the same existed options but for each option need two cases 'after' & 'from', ex:the option 'Bill of lading date' should be 'From Bill of lading date' and ' After Bill of lading date'. | 2024-02-28 | 2024-02-28
28 | lc advice event, with sight type | pending | only the option 'P-Payment' should be available in By Payment Term. | 2024-02-28 | 2024-02-28
29 | lc advice event, with usance type | pending | only the following options should be available in By Payment Term:'defferred', 'acceptance', 'mixed payment','negotiation'. | 2024-02-28 | 2024-02-28
30 | lc advice event. | Pass | this option'IRREVOCABLE TRANSFERABLE' to be added in Documentary Credit field. | 2024-02-28 | 2024-02-28
31 | LC advice with reimbursing bank | pending | for MT740 reimbursing bank we have two options for reimbursing charges OUR,CLM, so we need a check box to specify the type of reimbursing bank charge.(check the swift category). | 2024-02-29 | 2024-02-29
32 | bill lodgment. | pending | document type field should be optional. | 2024-02-29 | 2024-02-29
33 | Authorization to reimburse | pending | field 42a should be optional. | 2024-03-07 | 2024-03-07
34 | Authorization to reimburse | pending | the label 'payment details' should be ' Available With ... By ... ' | 2024-03-07 | 2024-03-07
35 | Authorization to reimburse | pending | (71A) Reimbursing Bank's Charges: we need only one field to specify if the charge 'CLM' or 'OUR', so remove the another field. | 2024-03-07 | 2024-03-07
36 | lc advice event. | pending | for mixed-payment type, the fileds 'usanse days' & 'from event' should be optional. | 2024-03-11 | 2024-03-11
37